## Gantt Chart
True North Senior Care — GHL Build Schedule
March 23 → April 6, 2026 · Sequential build: CRM schema → Pages → Automations → QA · Target: April 6 go-live
Task | Category | Start | End | Days | Mo 23 | Tu 24 | We 25 | Th 26 | Fr 27 | Sa 28 | Su 29 | Mo 30 | Tu 31 | We 1 | Th 2 | Fr 3 | Sa 4 | Su 5 | Mo 6
Phase 1 — CRM Foundation (Days 1–2)
Custom fields — all 4 funnels | CRM | 2026-03-23 | 2026-03-24 | 2 | bar: Mo 23 to Tu 24
Tags schema (source, class, nurture) | CRM | 2026-03-23 | 2026-03-24 | 2 | bar: Mo 23 to Tu 24
Lead scoring thresholds (<40/40–70/>70) | CRM | 2026-03-24 | 2026-03-24 | 1 | bar: Tu 24
Duplicate-handling rule (email match) | CRM | 2026-03-24 | 2026-03-24 | 1 | bar: Tu 24
Brand CSS + font import (global) | CRM | 2026-03-24 | 2026-03-25 | 2 | bar: Tu 24 to We 25
Nav + footer + compliance block | CRM | 2026-03-25 | 2026-03-25 | 1 | bar: We 25
Phase 2 — Pages & Funnels (Days 2–6)
Landing page — import ref HTML, wire nav | Pages | 2026-03-25 | 2026-03-26 | 2 | bar: We 25 to Th 26
Landing page — FAQ accordion + CTAs | Pages | 2026-03-26 | 2026-03-26 | 1 | bar: Th 26
Quiz — import HTML, map Q1–Q9 to fields | Pages | 2026-03-26 | 2026-03-27 | 2 | bar: Th 26 to Fr 27
Quiz — 3 results pages (score routing) | Pages | 2026-03-27 | 2026-03-28 | 2 | bar: Fr 27 to Sa 28
Calculator — import HTML, cost logic | Pages | 2026-03-27 | 2026-03-28 | 2 | bar: Fr 27 to Sa 28
Calculator — factor accordion + ins. CTA | Pages | 2026-03-28 | 2026-03-29 | 2
Guide — two-col layout, sticky form | Pages | 2026-03-28 | 2026-03-29 | 2
Guide — thank-you page + PDF card | Pages | 2026-03-29 | 2026-03-29 | 1 | bar: Su 29
Booking page — calendar embed (/book) | Pages | 2026-03-29 | 2026-03-30 | 2 | bar: Su 29 to Mo 30
Phase 3 — Automations & Email (Days 6–10)
Quiz intake workflow + lead scoring | Auto | 2026-03-30 | 2026-03-31 | 2 | bar: Mo 30 to Tu 31
Calculator intake workflow | Auto | 2026-03-30 | 2026-03-31 | 2 | bar: Mo 30 to Tu 31
Guide intake workflow | Auto | 2026-03-31 | 2026-04-01 | 2 | bar: Tu 31 to We 1
Cold nurture — 5 emails (Day 0–21) | Auto | 2026-03-31 | 2026-04-02 | 3 | bar: Tu 31 to Th 2
Warm nurture — 5 emails (Day 0–14) | Auto | 2026-04-01 | 2026-04-02 | 2 | bar: We 1 to Th 2
Hot follow-up — 3 emails + SMS | Auto | 2026-04-02 | 2026-04-03 | 2 | bar: Th 2 to Fr 3
Insurance CTA → partner notification | Auto | 2026-04-02 | 2026-04-03 | 2 | bar: Th 2 to Fr 3
Booking confirmation tag + notify | Auto | 2026-04-03 | 2026-04-03 | 1 | bar: Fr 3
Phase 4 — QA & Launch (Days 11–15)
Responsive QA — 375 / 768 / 1440px | QA | 2026-04-03 | 2026-04-04 | 2 | bar: Fr 3 to Sa 4
Form submit + CRM field mapping checks | QA | 2026-04-04 | 2026-04-04 | 1 | bar: Sa 4
Lead scoring spot-check (5 test leads) | QA | 2026-04-04 | 2026-04-05 | 2
Email merge fields + timing audit | QA | 2026-04-04 | 2026-04-05 | 2
Cost calc logic (all timeline combos) | QA | 2026-04-05 | 2026-04-05 | 1 | bar: Su 5
Full QA checklist — all 24 items | QA | 2026-04-05 | 2026-04-06 | 2 | bar: Su 5 to Mo 6
Go-live | QA | 2026-04-06 | 2026-04-06 | 1 | bar: Mo 6
| CRM foundation |  | Pages & funnels |  | Mo 23: Automations & email; We 25: QA & launch